## Intern1_CrawlEngine
Task ID | Feature | Task | Requirement ID | Requirement Description | Acceptance Criteria ID | Definition of Done | Est Days | Status
CE-001 | Project Setup | Setup Python project structure | NFR-001 | Deterministic architecture foundation | AC-017 | Project builds successfully and runs locally | 1 | Not Started
CE-002 | Project Setup | Configure JSONL logging framework | FR-022 | Structured JSON logging | AC-015 | Log file generated with required schema fields | 1 | Not Started
CE-003 | Project Setup | Create configuration loader | CFG-001 to CFG-009 | Config-driven execution | AC-017 | Config loads and validates successfully | 1 | Not Started
CE-004 | URL Discovery | Load seed URLs from configuration | FR-001 | Process seed URLs | AC-001 | Seed URLs loaded from config and queued | 1 | Not Started
CE-005 | URL Discovery | Implement BFS Queue Manager | FR-001 | BFS traversal | AC-001 | URLs processed in BFS order | 1 | Not Started
CE-006 | URL Discovery | Queue persistence support | FR-019 | Checkpoint queue state | AC-013 | Queue state saved and reloadable | 1 | Not Started
CE-007 | URL Discovery | Max depth enforcement | CFG-004 | Depth limits | AC-001 | Crawl stops beyond configured depth | 1 | Not Started
CE-008 | URL Discovery | Max page enforcement | CFG-005 | Page limits | AC-001 | Crawl stops after configured page count | 1 | Not Started
CE-009 | URL Discovery | Internal link extraction | FR-004 | Extract internal links | AC-002 | Internal links discovered correctly | 2 | Not Started
CE-010 | URL Discovery | External link detection | FR-005 | Ignore external links | AC-002 | External links skipped and logged | 1 | Not Started
CE-011 | URL Discovery | Allowed path filtering | FR-004 | Allowed path policy | AC-002 | Disallowed paths skipped | 1 | Not Started
CE-012 | Canonicalization | Lowercase scheme and host | FR-002 | URL normalization | AC-003 | Canonical URLs consistent | 1 | Not Started
CE-013 | Canonicalization | Remove URL fragments | FR-002 | URL normalization | AC-003 | Fragment URLs deduplicated | 1 | Not Started
CE-014 | Canonicalization | Remove tracking query params | FR-002 | URL normalization | AC-003 | Tracking parameters removed | 1 | Not Started
CE-015 | Canonicalization | Normalize trailing slashes | FR-002 | URL normalization | AC-003 | URL variants resolve to same key | 1 | Not Started
CE-016 | Canonicalization | Resolve relative URLs | FR-002 | URL normalization | AC-003 | Relative URLs become absolute URLs | 1 | Not Started
CE-017 | Canonicalization | Implement Seen URL registry | FR-003 | Process URL once | AC-001 | Duplicate URLs never recrawled | 1 | Not Started
CE-018 | Canonicalization | Unit tests for canonicalization | FR-002, FR-003 | Validation | AC-003 | Test suite passes | 1 | Not Started
CE-019 | HTML Extraction | Build HTTP Fetch Service | FR-006 | Download HTML pages | AC-004 | HTML content downloaded successfully | 2 | Not Started
CE-020 | HTML Extraction | Request timeout handling | CFG-006 | Timeout support | AC-012 | Requests timeout correctly | 1 | Not Started
CE-021 | HTML Extraction | Retry with exponential backoff | FR-018 | Retry transient failures | AC-012 | Retries follow configured policy | 2 | Not Started
CE-022 | HTML Extraction | HTML parser implementation | FR-006 | Parse page content | AC-004 | HTML parsed without errors | 1 | Not Started
CE-023 | HTML Extraction | Page title extraction | FR-007 | Metadata extraction | AC-004 | Title stored in metadata | 1 | Not Started
CE-024 | HTML Extraction | Main content extraction | FR-006 | Extract content | AC-004 | Main content extracted accurately | 2 | Not Started
CE-025 | HTML Extraction | Navigation/noise removal | FR-006 | Content cleanup | AC-004 | Noise removed from extracted content | 1 | Not Started
CE-026 | HTML Extraction | Metadata extraction | FR-007 | Frontmatter metadata | AC-004 | Required metadata captured | 1 | Not Started
CE-027 | Markdown Storage | HTML to Markdown conversion | FR-006 | Markdown artifact creation | AC-004 | Content converted successfully | 2 | Not Started
CE-028 | Markdown Storage | YAML frontmatter generation | FR-007 | Metadata contract | AC-004 | All required frontmatter fields present | 1 | Not Started
CE-029 | Markdown Storage | URL-to-path mapping | FR-006 | Deterministic storage | AC-004 | Path structure generated correctly | 2 | Not Started
CE-030 | Markdown Storage | Raw folder creation | FR-006 | Storage structure | AC-004 | Folders auto-created | 1 | Not Started
CE-031 | Markdown Storage | Atomic file write support | FR-008 | Safe writes | AC-005 | No corrupt partial files | 1 | Not Started
CE-032 | Markdown Storage | Content hash generation | FR-009 | Change detection | AC-006 | Hash generated consistently | 1 | Not Started
CE-033 | Markdown Storage | Skip unchanged content | FR-009 | Idempotency | AC-006 | No rewrite when content unchanged | 1 | Not Started
CE-034 | Markdown Storage | Save markdown artifacts | FR-006, FR-007 | Artifact persistence | AC-004 | Markdown file saved successfully | 1 | Not Started
CE-035 | Reliability | Crawl workflow integration | FR-001 to FR-009 | End-to-end crawl | AC-001 to AC-006 | Crawl completes successfully | 2 | Not Started
CE-036 | Reliability | Checkpoint save and reload | FR-019, FR-020 | Resume support | AC-013 | Resume continues correctly after restart | 2 | Not Started
CE-037 | Reliability | Structured event logging | FR-022, FR-023 | Audit logging | AC-015 | All events logged with required fields | 1 | Not Started
CE-038 | Reliability | Failure isolation | FR-021 | Continue after failure | AC-014 | Single page failure doesn't stop crawl | 1 | Not Started
CE-039 | Testing | Unit Test Suite | Test Strategy | Unit validation | AC-001 to AC-006 | All unit tests pass | 3 | Not Started
CE-040 | Testing | Integration Test Suite | Test Strategy | End-to-end validation | AC-001 to AC-016 | All integration tests pass | 2 | Not Started
CE-041 | Testing | Determinism Validation | NFR-001 | Deterministic output | AC-017 | Two identical runs produce same results | 1 | Not Started
CE-042 | Testing | Idempotency Validation | NFR-002 | No duplicate artifacts | AC-018 | Reruns do not create duplicates | 1 | Not Started
CE-043 | Testing | Provenance Validation | NFR-005 | Source traceability | AC-019 | All artifacts contain provenance fields | 1 | Not Started
CE-044 | Testing | Reliability Validation | NFR-007 | Continue despite failures | AC-020 | Pipeline survives bounded failures | 1 | Not Started
CE-045 | Documentation | Developer Runbook | Definition of Done | Operational guide | DoD | Runbook created and reviewed | 2 | Not Started